### Sprint Summary - LibreHealth EHR Training Videos.

Summary: the proposal was to produce the first three videos of the list I submitted. I completed the first two videos and the third is in production pending code revisions. Completed work has been posted to the LibreEHR YouTube site.

1. Entering a new patient. Description: "This set of tasks reqires a computer- competant manager/ EHR Administrator to configure such items as required demographics fields, and customize certain demographics and other patient data fields."

As stated in my prelimnary proposal, a separate, different video was envisioned for the Front Desk / Reception Staff Data- Entry level workflow which in my original intentions included the full patient history, Issues and historical medications. However, @rhoyt mentioned he wanted the patient history entry added to this video. That is feasible without pushing the total video time past the max effective time of 10 - 15 minutes.

Status: I will move that addition to the next sprint.
Current video found at: https://youtu.be/x_kn--DoJwI

2. Creating a new encounter. Description: "Encounters require an EHR Administrator workflow to set the default system behaviors, and a Staff workflow performed by both Front Desk and Provider staff to conduct the steps of the encounter. Granted this is the most generic encounter worflow possible."

Status: completed
Video found at: https://youtu.be/kCVt1qPPthE

3. How to use the calendar. Description: User activities with a pre-configured Calendar; "Am going to include the flow board in this one since the flowboard functionality is such a tremendous benefit to efficient clinic function and configuring the calendar is 75% of configuring the flowboard."

Status: In progress; shifted to next sprint.. Bugs/ suboptimal behaviors were discovered in patient display from the flow board and calendar; need addition of event parameters to the calendar configuration module; possible other mods in the works that might be included in this video unless added later.

Regards- Harley Tuck